## Sheet1
PyGame POC – Effort Estimation
Task | Hours | Notes
Minimal project scaffold | 1 | Create simple frontend, backend, and runtime folders with basic local commands.
Simple frontend UI | 2 | One screen with textarea/code editor, Run, Stop, terminal output area, and game display iframe.
noVNC display integration | 2 | Use existing noVNC client and connect directly to local websockify URL exposed from Docker. No custom proxy.
Node backend basic setup | 2 | Create Express backend with /run and /stop endpoints.
Code write and run orchestration | 2 | Backend writes submitted code to main.py and starts the Docker runtime command.
Terminal stdout/stderr streaming | 2 | Stream Python process output back to frontend using a simple WebSocket or server-sent event style flow.
Docker pygame runtime | 3 | Build Docker image with Python, pygame, Xvfb, x11vnc, and websockify.
Runtime launcher script | 1 | Start Xvfb, x11vnc, websockify, set DISPLAY, and run python main.py.
End-to-end demo testing | 1 | Validate Run, visual streaming, terminal output, Stop, and one rerun.
Total | 16